TECHNICAL SPECIFICATION

&

PROJECT PLAN

Highland Bagpiper

www.highlandbagpiper.io

Professional Bagpiper Booking Platform

Tech Stack: Next.js · Vercel · Convex · Convex Auth

MVP Pilot Market: New Zealand & Australia

Confidential

March 2026 · Version 1.0

# Table of Contents

Note: Update this table of contents after opening in Word (right-click → Update Field).

PART A: TECHNICAL SPECIFICATION

# 1. Project Overview

## 1.1 Purpose

Highland Bagpiper is a specialist two-sided marketplace connecting professional Highland bagpipers with clients seeking piping services for weddings, funerals, ceremonies, corporate events, and cultural celebrations. The platform addresses a fragmented market currently dominated by word-of-mouth referrals, enabling pipers to be fairly compensated and clients to discover, evaluate, and book quality pipers with confidence.

## 1.2 Current State

The following features are currently built and deployed at www.highlandbagpiper.io:

| Feature | Status | Notes |
| --- | --- | --- |
| Landing page / marketing site | ✓ Complete | Deployed on Vercel |
| Piper registration & profile creation | ✓ Complete | Convex Auth + Convex DB |
| Client search & discovery of pipers | ✓ Complete | Browse/search piper listings |
| Booking request / enquiry flow | ✓ Complete | Client can submit booking request |
| Messaging (piper ↔ client) | ✗ Not built | Critical for consultative bookings |
| Payment processing | ✗ Not built | Stripe integration needed |
| Reviews / ratings system | ✗ Not built | Post-event review workflow |
| Admin dashboard | ✗ Not built | Platform oversight & moderation |
| Piper dashboard / booking management | ✗ Not built | Calendar, bookings, earnings |
| Event brief / quote workflow | ✗ Not built | Structured event details + pricing |
| Email notifications | ✗ Not built | Transactional emails (Resend/Postmark) |

## 1.3 Technology Stack

| Layer | Technology | Details |
| --- | --- | --- |
| Frontend | Next.js (App Router) | React 18+, TypeScript, Tailwind CSS |
| Hosting | Vercel | Edge deployment, automatic CI/CD from Git |
| Backend / Database | Convex | Real-time serverless backend, document DB, file storage |
| Authentication | Convex Auth | Built-in auth with Convex’s native auth system |
| Source Control | Git | Repository linked to Vercel for auto-deploys |
| Development | VS Code + Claude Code | AI-assisted development workflow |
| Payments (Planned) | Stripe | Connect for marketplace payouts to pipers |
| Email (Planned) | Resend or Postmark | Transactional email delivery |
| File Storage | Convex File Storage | Profile images, audio/video samples |

# 2. System Architecture

## 2.1 High-Level Architecture

The application follows a modern serverless architecture with Convex as the unified backend layer handling database, real-time subscriptions, file storage, and server-side logic (mutations/queries/actions). Next.js serves as the frontend rendering layer deployed on Vercel’s edge network.

Data Flow: Client Browser → Next.js (Vercel Edge) → Convex Client SDK → Convex Backend (queries/mutations) → Convex Database. Real-time updates flow back via Convex’s reactive subscription model, giving users live data without polling.

## 2.2 Convex Data Schema

The following schema defines the core data model. This should be implemented in convex/schema.ts:

Users Table

Extends Convex Auth’s built-in user record with role-specific fields:

users: { role: "piper" | "client" | "admin", email: string, name: string,

phone?: string, profileImageId?: Id<"_storage">, createdAt: number,

lastLoginAt?: number, isActive: boolean, onboardingComplete: boolean }

Piper Profiles Table

Rich profile data for each piper’s public listing:

piperProfiles: { userId: Id<"users">, displayName: string, bio: string,

location: { city: string, region: string, country: string, lat?: number, lng?: number },

serviceRadius: number (km), willingToTravel: boolean,

experience: { yearsPlaying: number, competitionHistory?: string,

grade?: string, associations?: string[], pipeBand?: string },

services: { eventTypes: string[], dressOptions: string[], repertoire?: string[] },

pricing: { baseFee: number, currency: "NZD"|"AUD"|"GBP"|"USD"|"EUR"|"CAD",

travelRatePerKm?: number, additionalCosts?: string },

media: { photoIds: Id<"_storage">[], audioIds?: Id<"_storage">[],

videoUrls?: string[] },

availability: { calendar?: object, blackoutDates?: string[] },

verified: boolean, featuredPiper: boolean, stripeAccountId?: string }

Bookings Table

The core transactional record linking client to piper:

bookings: { clientId: Id<"users">, piperId: Id<"users">,

piperProfileId: Id<"piperProfiles">,

status: "enquiry"|"quoted"|"accepted"|"deposit_paid"|"confirmed"

|"completed"|"cancelled"|"disputed",

eventDetails: { type: string, date: string, time: string,

endTime?: string, duration: number (minutes),

venue: { name: string, address: string, city: string,

region: string, country: string, indoorOutdoor: string },

guestCount?: number, specialRequirements?: string },

musicPreferences: { tunes?: string[], genre?: string, notes?: string },

dressPreference?: string,

quote: { performanceFee?: number, travelFee?: number,

accommodationFee?: number, totalFee?: number,

currency: string, notes?: string, validUntil?: string },

payment: { depositAmount?: number, depositPaidAt?: string,

finalAmount?: number, finalPaidAt?: string,

stripePaymentIntentId?: string, stripeTransferId?: string },

createdAt: number, updatedAt: number }

Messages Table

Real-time messaging between piper and client per booking:

messages: { bookingId: Id<"bookings">, senderId: Id<"users">,

content: string, attachmentIds?: Id<"_storage">[],

readAt?: number, createdAt: number }

Reviews Table

reviews: { bookingId: Id<"bookings">, reviewerId: Id<"users">,

piperId: Id<"users">, rating: number (1–5),

title?: string, content: string,

response?: string, createdAt: number }

Supporting Tables

notifications: { userId: Id<"users">, type: string,

title: string, message: string, linkTo?: string,

readAt?: number, createdAt: number }

auditLog: { userId?: Id<"users">, action: string,

entityType: string, entityId: string,

metadata?: object, createdAt: number }

## 2.3 Indexes

The following Convex indexes are recommended for query performance:

- piperProfiles: by_country, by_region, by_userId, by_verified

- bookings: by_clientId, by_piperId, by_status, by_date

- messages: by_bookingId, by_senderId

- reviews: by_piperId, by_bookingId

- notifications: by_userId_unread

# 3. Feature Specifications

## 3.1 Messaging System

This is the highest-priority feature to build. Piping engagements require detailed consultation before a booking can be confirmed. The messaging system must support:

- Real-time message delivery using Convex’s reactive queries (useQuery on messages filtered by bookingId).

- Text messages with optional file attachments (photos of venue, sheet music) via Convex file storage.

- Message thread tied to each booking/enquiry, accessible from both piper and client dashboards.

- Unread message count badges and in-app notification indicators.

- Email notification when a new message is received (with configurable frequency: instant, daily digest, or off).

- Message history preserved for the life of the booking for dispute resolution.

Implementation: Create a Convex mutation sendMessage and a query getMessagesByBooking. Use Convex’s real-time subscriptions on the client side for instant updates. Build a ChatPanel React component that can be embedded in the booking detail view.

## 3.2 Event Brief & Quote Workflow

This structured workflow replaces ad-hoc email coordination and captures all details needed for a piping engagement:

Step 1: Client Submits Event Brief (extends existing enquiry flow)

- Event type (wedding ceremony, funeral, Burns Night, corporate, etc.)

- Date, start time, estimated duration

- Venue details (name, address, indoor/outdoor)

- Guest count (approximate)

- Music preferences (traditional, specific tunes, processional/recessional requirements)

- Dress preference (No. 1 Highland dress, No. 2, specific tartan if required)

- Budget indication (optional range)

- Special requirements (accessibility, amplification, multiple locations within venue)

Step 2: Piper Reviews Brief & Sends Quote

- Piper receives notification of new enquiry with full event brief.

- Piper can ask clarifying questions via messaging before quoting.

- Piper builds itemised quote via structured form: performance fee, travel costs, accommodation if required, preparation/rehearsal fee for special tune requests, total.

- Quote includes validity period (e.g. 7 days) and cancellation terms.

Step 3: Client Accepts & Pays Deposit

- Client reviews itemised quote, can request adjustments via messaging.

- On acceptance, client pays deposit (typically 50%) via Stripe.

- Both parties receive confirmation with agreed details.

- Booking status moves to ‘confirmed’.

## 3.3 Payment Processing (Stripe Connect)

The platform will use Stripe Connect in ‘Express’ mode to handle marketplace payments:

- Piper Onboarding: During profile setup, pipers connect a Stripe Express account. Convex action triggers Stripe account creation and stores the stripeAccountId.

- Deposit Payment: When client accepts a quote, Stripe creates a PaymentIntent with application_fee_amount (platform commission, e.g. 12%) and transfer_data pointing to the piper’s connected account.

- Final Payment: Remaining balance charged 7 days before event date (or on a schedule agreed in the booking terms).

- Piper Payouts: Stripe handles payouts to the piper’s bank account on the standard payout schedule (typically 2 business days after payment).

- Refunds & Disputes: Platform admin can process full or partial refunds. Cancellation policy enforced: full refund if cancelled 14+ days before event, 50% if 7–14 days, no refund if under 7 days (configurable).

Stripe Connect supports NZD, AUD, GBP, USD, CAD, and EUR — covering all target markets. For the NZ/Australia pilot, Stripe operates natively in both countries.

## 3.4 Reviews & Ratings

- After a booking reaches ‘completed’ status, the client receives an email prompting them to leave a review.

- Reviews include a 1–5 star rating plus written feedback.

- Pipers can post a public response to each review.

- Average rating displayed on piper profile cards and detail pages.

- Minimum of 3 reviews before aggregate rating is displayed publicly (to avoid single-review distortion).

- Admin can moderate reviews for inappropriate content.

## 3.5 Piper Dashboard

A dedicated dashboard for pipers to manage their business on the platform:

- Booking Overview: List of all enquiries, active bookings, and past engagements with status indicators.

- Calendar View: Visual calendar showing confirmed bookings and blocked dates. Pipers can mark dates as unavailable.

- Earnings Summary: Total earned, pending payouts, commission breakdown, and Stripe payout history.

- Profile Management: Edit bio, media, repertoire, pricing, and availability.

- Notifications Centre: All booking requests, messages, reviews, and system notifications.

- Performance Analytics: Profile views, enquiry conversion rate, average rating, repeat client rate.

## 3.6 Client Dashboard

- My Bookings: Active and past bookings with status tracking.

- Messages: Consolidated view of all conversations with pipers.

- Saved Pipers: Shortlist/favourites functionality.

- Leave Reviews: Prompt to review completed bookings.

## 3.7 Admin Dashboard

- User Management: View all pipers and clients, activate/deactivate accounts, verify piper profiles.

- Booking Oversight: Monitor active bookings, intervene in disputes, process refunds.

- Review Moderation: Flag/remove inappropriate reviews.

- Platform Metrics: Total bookings, GMV, revenue, active users, conversion rates.

- Content Management: Update landing page content, featured pipers, blog posts.

## 3.8 Email Notifications

Transactional emails triggered by platform events, sent via Resend (recommended for Vercel/Next.js integration) or Postmark:

| Trigger | Recipient | Content |
| --- | --- | --- |
| New enquiry received | Piper | Event brief summary + link to respond |
| Quote sent | Client | Itemised quote + link to accept/discuss |
| Quote accepted / deposit paid | Piper | Confirmation + booking details |
| New message received | Both | Message preview + link to conversation |
| Event reminder (48hr before) | Both | Event details summary + contact info |
| Event completed — leave review | Client | Review prompt + link |
| New review received | Piper | Review content + link to respond |
| Booking cancelled | Both | Cancellation details + refund info |
| Payout processed | Piper | Amount + Stripe payout reference |

## 3.9 NZ/Australia Localisation

For the pilot market launch, the following localisations are required:

- Currency: NZD and AUD as primary currencies, with correct formatting ($X.XX).

- Geography: Region/city data for NZ (16 regions) and Australia (6 states + 2 territories). Location-based piper search.

- Time zones: NZST/NZDT and AEST/ACST/AWST handling for booking dates and event reminders.

- Content: Landing page copy referencing NZ/Australian piping community, Highland Games (e.g. Waipu, Bundanoon), and local pipe band associations (RNZPBA, Pipe Bands Australia).

- Legal: NZ and Australian consumer protection compliance, privacy policy aligned with NZ Privacy Act 2020 and Australian Privacy Act 1988.

- Stripe: Both NZ and Australia are supported Stripe Connect countries with native bank payouts.

# 4. Non-Functional Requirements

- Performance: Pages should load within 2 seconds on 4G connections. Convex’s edge caching and Vercel’s CDN provide strong baseline performance.

- Scalability: Convex handles horizontal scaling automatically. No infrastructure management required for the pilot phase.

- Security: All data encrypted in transit (HTTPS) and at rest (Convex managed). Convex Auth handles session management and CSRF protection. Stripe handles PCI compliance for payment data.

- Availability: Vercel and Convex both provide 99.9%+ uptime SLAs. No additional redundancy required for MVP.

- Mobile Responsiveness: All pages must be fully responsive. Target devices: iPhone SE (smallest) through iPad. Tailwind CSS mobile-first approach.

- SEO: Server-side rendering via Next.js for piper profile pages and landing pages to ensure search engine discoverability. Open Graph meta tags for social sharing.

- Accessibility: WCAG 2.1 AA compliance target. Semantic HTML, ARIA labels, keyboard navigation, sufficient colour contrast.

- Data Privacy: GDPR-aligned data handling even for NZ/AU launch (future-proofing for UK/EU expansion). User data export and deletion capabilities.

PART B: PROJECT PLAN

# 5. Project Phases & Timeline

The project is structured into four phases, progressing from completing the MVP feature set through pilot testing to market launch. Timeline assumes part-time development using VS Code + Claude Code, with approximately 15–20 hours per week of development effort.

## 5.1 Phase 1: Complete MVP Core (Weeks 1–4)

Goal: Build the minimum features required to facilitate a real end-to-end booking between a piper and a client.

| # | Task | Effort | Dependency | Priority |
| --- | --- | --- | --- | --- |
| 1.1 | Messaging system (real-time chat per booking) | 8–12 hours | None | Critical |
| 1.2 | Enhanced event brief form (structured fields) | 4–6 hours | None | Critical |
| 1.3 | Quote builder for pipers (itemised pricing) | 6–8 hours | 1.2 | Critical |
| 1.4 | Booking status workflow (state machine) | 4–6 hours | 1.3 | Critical |
| 1.5 | Piper dashboard (bookings list, calendar view) | 8–10 hours | 1.4 | Critical |
| 1.6 | Client dashboard (my bookings, messages) | 6–8 hours | 1.4 | Critical |
| 1.7 | Email notifications (Resend integration — core events) | 6–8 hours | 1.4 | High |
| 1.8 | NZ/AU localisation (currencies, regions, timezones) | 4–6 hours | None | High |

Estimated Phase 1 Effort: 46–64 hours (3–4 weeks at 15–20 hrs/week)

Deliverable: A fully functional booking flow where a client can discover a piper, submit an event brief, exchange messages, receive a quote, and confirm a booking.

## 5.2 Phase 2: Payments & Trust (Weeks 5–8)

Goal: Enable real financial transactions and build trust mechanisms.

| # | Task | Effort | Dependency | Priority |
| --- | --- | --- | --- | --- |
| 2.1 | Stripe Connect integration (Express accounts) | 10–14 hours | Phase 1 | Critical |
| 2.2 | Deposit payment flow (client pays on quote acceptance) | 8–10 hours | 2.1 | Critical |
| 2.3 | Final payment / balance collection | 4–6 hours | 2.2 | High |
| 2.4 | Reviews & ratings system | 8–10 hours | Phase 1 | High |
| 2.5 | Piper earnings dashboard (payouts, commission visibility) | 4–6 hours | 2.2 | High |
| 2.6 | Cancellation & refund workflow | 4–6 hours | 2.2 | Medium |
| 2.7 | Terms of Service & Privacy Policy pages | 3–4 hours | None | High |

Estimated Phase 2 Effort: 41–56 hours (3–4 weeks at 15–20 hrs/week)

Deliverable: Complete transactional platform with real payments, piper payouts, and post-event reviews.

## 5.3 Phase 3: Pilot Testing (Weeks 9–14)

Goal: Test the platform with real pipers and clients in New Zealand and Australia.

| # | Task | Effort | Dependency | Priority |
| --- | --- | --- | --- | --- |
| 3.1 | Recruit 10–20 pilot pipers (NZ: RNZPBA network, AU: Pipe Bands Australia) | 10–15 hours | Phase 2 | Critical |
| 3.2 | Piper onboarding support (help create profiles, connect Stripe) | 8–10 hours | 3.1 | Critical |
| 3.3 | Seed 3–5 test bookings with friendly clients | 5–8 hours | 3.2 | Critical |
| 3.4 | Bug fixes and UX refinements from pilot feedback | 15–25 hours | 3.3 | Critical |
| 3.5 | Admin dashboard (basic: user list, booking overview, metrics) | 8–10 hours | Phase 2 | High |
| 3.6 | Collect pilot piper and client testimonials | 3–5 hours | 3.3 | Medium |
| 3.7 | Analytics setup (Vercel Analytics / Plausible / PostHog) | 2–4 hours | None | Medium |

Estimated Phase 3 Effort: 51–77 hours (5–6 weeks, mixed dev and outreach)

Deliverable: Validated platform with real transactions, user feedback, and data to inform marketing strategy.

## 5.4 Phase 4: Marketing Readiness & Launch (Weeks 15–20)

Goal: Prepare for public launch with marketing plan, SEO, and growth features.

| # | Task | Effort | Dependency | Priority |
| --- | --- | --- | --- | --- |
| 4.1 | SEO optimisation (SSR piper profiles, meta tags, structured data) | 6–8 hours | Phase 3 | Critical |
| 4.2 | Landing page refresh with testimonials and pilot data | 4–6 hours | 3.6 | High |
| 4.3 | Blog / content section (piping guides, booking tips) | 6–8 hours | None | Medium |
| 4.4 | Social media integration (share piper profiles) | 2–4 hours | None | Medium |
| 4.5 | Google Business Profile + local SEO for key NZ/AU cities | 3–5 hours | None | High |
| 4.6 | Develop marketing plan (separate deliverable) | 8–12 hours | Phase 3 data | Critical |
| 4.7 | Scale piper recruitment to 50–100 across NZ/AU | 15–20 hours | 3.6 | Critical |
| 4.8 | UK market preparation (localisation, initial outreach) | 6–8 hours | Phase 3 | Medium |

Estimated Phase 4 Effort: 50–71 hours (5–6 weeks)

Deliverable: Public launch-ready platform with marketing plan, SEO foundation, and growing piper base.

# 6. NZ/Australia Pilot Testing Plan

## 6.1 Pilot Objectives

- Validate the end-to-end booking flow with real users and real money.

- Identify UX friction points in the piper-client coordination process.

- Test payment processing (Stripe Connect) with NZD and AUD transactions.

- Gather testimonials and case studies for marketing.

- Measure key metrics: time from enquiry to confirmed booking, booking completion rate, average booking value, user satisfaction.

## 6.2 Target Pilot Pipers

New Zealand and Australia have active but relatively small piping communities, making them ideal for a focused pilot:

- New Zealand: Approach pipers through the RNZPBA network, targeting Auckland, Wellington, Christchurch, and Dunedin (strong Scottish heritage city). Highland Games at Waipu and Hastings are good recruitment events.

- Australia: Focus on Victoria (strongest piping state — home to Hawthorn Pipe Band, a Grade 1/2 competitor), NSW (The Pipe Band Club, Sydney), and Queensland. Pipe Bands Australia coordinates six state associations.

- Target 10–20 pipers with: active event performance experience, professional presentation (Highland dress, online presence), willingness to trial a new platform, and ideally existing client flow to redirect through the platform.

## 6.3 Pilot Metrics & Success Criteria

| Metric | Target (6-week pilot) | How Measured |
| --- | --- | --- |
| Pipers onboarded | 10–20 with complete profiles | Convex DB count |
| Enquiries received | 15–30 total | Booking records with status ≥ enquiry |
| Bookings confirmed | 5–10 with deposit paid | Stripe payment records |
| Enquiry → booking conversion | >30% | Confirmed / total enquiries |
| Avg. booking value | $300–$500 NZD/AUD | Stripe transaction data |
| User satisfaction (pipers) | >4/5 average | Post-pilot survey |
| User satisfaction (clients) | >4/5 average | Post-event survey + reviews |

# 7. Risk Register

| Risk | Likelihood | Impact | Mitigation | Owner |
| --- | --- | --- | --- | --- |
| Low pilot piper recruitment | Medium | High | Personal outreach via pipe band networks; offer zero commission for pilot | Founder |
| Stripe Connect onboarding friction | Medium | Medium | Provide step-by-step guide; offer 1:1 onboarding support calls | Founder / Dev |
| Users bypass platform for direct payment | High | High | Deliver genuine value (contracts, payment protection, reviews) that justifies commission | Product |
| Insufficient client-side demand during pilot | Medium | Medium | Seed initial bookings via piper networks; targeted social media ads in NZ/AU | Founder |
| Convex service outage | Low | High | Convex 99.9% SLA; no mitigation needed for MVP beyond monitoring | Dev |
| Scope creep delays MVP | High | Medium | Strict phase gates; ship Phase 1 before starting Phase 2 | Founder |
| Payment disputes / chargebacks | Low | Medium | Clear T&Cs, cancellation policy, Stripe Radar fraud detection | Dev / Legal |

# 8. Summary Timeline

| Phase | Timeline | Key Deliverable | Milestone |
| --- | --- | --- | --- |
| Phase 1: MVP Core | Weeks 1–4 | Complete booking flow with messaging | First end-to-end test booking |
| Phase 2: Payments & Trust | Weeks 5–8 | Stripe payments + reviews | First real money transaction |
| Phase 3: Pilot Testing | Weeks 9–14 | 10–20 pipers, 5–10 bookings | Validated product-market fit |
| Phase 4: Launch Readiness | Weeks 15–20 | SEO, marketing plan, scale | Public launch NZ/AU |

Total estimated timeline: ~20 weeks (5 months) from today to public launch, at 15–20 hours/week development effort.

Total estimated development effort: 188–268 hours across all phases.

# 9. Immediate Next Steps

To begin Phase 1 development this week:

- 1. Schema update: Review and extend your Convex schema.ts to include the messages, reviews, notifications, and enhanced bookings tables defined in Section 2.2.

- 2. Messaging MVP: Build the real-time chat component. Start with a Convex mutation (sendMessage) and query (getMessagesByBooking), then build a ChatPanel React component with Tailwind styling.

- 3. Event brief enhancement: Extend your existing booking request form with the structured fields from Section 3.2 (venue details, music preferences, dress options).

- 4. Quote builder: Create a piper-facing form that generates an itemised quote linked to a booking, with fee breakdown and validity period.

- 5. Resend account setup: Create a Resend account, verify your domain (highlandbagpiper.io), and implement the first transactional email template (new enquiry notification).

- 6. Stripe account: Create a Stripe account and enable Connect. Start in test mode during Phase 1; go live at the start of Phase 2.

End of Document

Highland Bagpiper — Technical Specification & Project Plan — March 2026 v1.0